## Trang_tính1
CAPSTONE FINAL : AIR BNB REACT JS
STT | Task Name | Start Build | Finish Build | %Build | Names Dev | Start Testing | Finish Testing | % Testing | Names Dev | Notes
| ADMIN |  |  | 100% | Nguyen Thi Be Ngoan |  |  | 100% | Nguyen Thi Be Ngoan | Completed
1 | Login | 2024-04-20 | 2024-04-22 |  |  | 2024-04-25 | 2024-04-30
| HeaderAdmin |  |  |  |  | 2024-04-30 | 2024-05-15
| 1.ConfimLogout* | 2024-04-25 | 2024-04-28
| 2.Notification | 2024-04-27 | 2024-04-28
| 3.Profile |  | 2024-04-30
4.ProfileModal
| 5.Theme* | 2024-04-30 | 2024-05-05
| 6.Hamburger |  | 2024-05-01
3 | DashBoard | 2024-05-01 |  |  |  | 2024-05-08 | 2024-05-14
4 | RoomTable* |  | 2024-05-08
5 | LocationTable | 2024-05-03 | 2024-05-07
6 | BookingTable |  | 2024-05-08
7 | Button | 2024-05-02
| 1.Create |  | 2024-05-06 |  |  | 2024-05-10 | 2024-05-15
| 2.Delete |  | 2024-05-07
| 3.Update* |  | 2024-05-08 |  |  | 2024-05-12 | 2024-05-16
8 | ChartAdmin | 2024-05-04 |  |  |  | 2024-05-10 | 2024-05-13
| 1.ChartPie** |  | 2024-05-09
| 2.ChartLine* |  | 2024-05-10
9 | UserTable* | 2024-05-06 | 2024-05-16 |  |  | 2024-05-16 | 2024-05-16
10 | LoadingPage | 2024-05-09 | 2024-05-15 |  |  | 2024-05-15 | 2024-05-16
11 | SidebarAdmin** | 2024-05-06 | 2024-05-12 |  |  | 2024-05-12 | 2024-05-16
| USER |  |  | 100% | Nguyen Anh Truyen |  |  | 100% | Nguyen Anh Truyen | Completed
1 | HomePage
| 1.Header | 2024-04-25 | 2024-04-26 |  |  | 2024-04-28 | 2024-04-29
| 2.Footer | 2024-04-26 | 2024-04-27
| 3.ListRoom | 2024-04-26 | 2024-04-28 |  |  | 2024-04-29 | 2024-04-30
| 4.ListViTri | 2024-04-28 | 2024-04-30
| 5.Anywhere | 2024-04-29 | 2024-04-30 |  |  | 2024-05-01 | 2024-05-02
| 6.Modal | 2024-04-29 | 2024-05-01
2 | Input | 2024-04-30 | 2024-05-01 |  |  | 2024-05-03 | 2024-05-03
3 | DetailPage | 2024-05-02 | 2024-05-06 |  |  | 2024-05-07 | 2024-05-09
4 | UserInfo* | 2024-05-02 | 2024-05-12 |  |  | 2024-05-10 | 2024-05-14
5 | VitriPage* | 2024-05-05 | 2024-05-13 |  |  | 2024-05-12 | 2024-05-16
DEPLOY WEB VERCEL |  | Nguyen Thi Be Ngoan Nguyen Anh Truyen